## Tracker
Feature ID | Feature Name | Area / Module | Source File(s) | Route / Screen / Command / Entry Point | User Type | User Story | Expected Behaviour | Actual Behaviour | Status | Test Type | Test Steps | Test Result | Error / Bug Found | Severity | Fix Required | Fix Implemented | Files Changed | Commit Hash | Retest Steps | Retest Result | Final Status | Product Decision Needed | Notes | Original Prompt
PUB-001 | Canonical agent brief live verification anchor | Public Agent Documentation | llms-full.txt | Public llms-full.txt | Agent integrator | As an agent integrator, I want the canonical brief to identify the latest verified production state, so that I do not treat older deployment evidence as current. | The primary anchor reflects the July 15 calculation-plane evidence and July 16 discovery while retaining July 2 as historical context. | The July 15 v11 brief still called the July 2 revision the most recent verification anchor. | Fixed | Static contract comparison and executable regression | Compare llms-full.txt with live discovery and July 15 receipts. | FAIL — primary verification anchor was stale. | Latest-anchor heading and evidence were stale. | High | Yes | Promoted the July 15/16 verification block and retained July 2 as historical Synthetic AI10 context. | llms-full.txt | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-002 | Landing-page OpenAPI and MCP inventory | Public Landing Page | index.html | Live contract snapshot and reference cards | Developer | As a developer, I want the landing page to show the current live contract inventory, so that I can plan an integration accurately. | Landing copy reports 68 paths, 81 tools, 26 semantic tools, 30 priced routes, and 47 fields. | The landing page reported 48 paths and omitted the governed semantic catalog. | Fixed | Static contract comparison and executable regression | Compare landing counts with captured live discovery. | FAIL — documented route and tool inventory was stale. | Stale public route and tool counts. | High | Yes | Updated both route claims and added the semantic MCP inventory. | index.html | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-003 | Expanded issuer calculation-universe disclosure | Public Coverage Documentation | index.html; llms-full.txt; README.md | Coverage and capability sections | Research user | As a research user, I want current calculation coverage separated from historical cohorts, so that I do not confuse an older snapshot with the active universe. | Current copy identifies 378 issuers as 215 crypto-canonical plus 163 expanded issuers and labels 312/298 as historical. | The public surfaces described the 312/298 snapshot as current expanded coverage. | Fixed | Static contract comparison and executable regression | Compare coverage prose with the July 15 replay receipt. | FAIL — current and historical cohorts were conflated. | Coverage cohort drift. | High | Yes | Published the 378-row current universe and retained 312/298 only as historical context. | index.html; llms-full.txt; README.md | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-004 | Level 2 replay and customer-audit receipts | Public Evidence Documentation | index.html; llms-full.txt; llms.txt; README.md | July verification blocks | Operator | As an operator, I want bounded replay and audit receipts, so that I can distinguish calculation-plane completion from customer-route health. | Public copy reports 378/378, 817,992 rows, 0 errors and separately 215 issuers, 1,935 operations, 1,923 successful, 0 failed. | The final replay and zero-failure audit summary were absent. | Fixed | Static contract comparison and executable regression | Compare public copy with final_live_receipts.json. | FAIL — final operational receipts were missing. | Current public operational evidence was incomplete. | High | Yes | Added bounded replay/audit receipts and an explicit scope boundary. | index.html; llms-full.txt; llms.txt; README.md | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-005 | Governed semantic MCP guidance | Semantic MCP Documentation | README.md; index.html; llms-full.txt; server.json; .codex-plugin/plugin.json | Public semantic discovery and query guidance | Agent developer | As an agent developer, I want catalog-first semantic-query guidance, so that I use allowlisted fields and preserve evidence boundaries. | Docs identify 26 atlas7_* tools, catalog-first query planning, evidence envelopes, subscription gating, and no raw SQL. | The public plugin omitted the governed semantic surface from its primary integration guidance. | Fixed | Static contract comparison and executable regression | Compare documented semantic tools with public MCP tools/list. | FAIL — 26 live semantic tools were not represented in the primary contract. | Semantic discovery drift. | High | Yes | Added semantic model/field catalog, compile/query, lineage, gating, and evidence-envelope guidance. | README.md; index.html; llms-full.txt; server.json; .codex-plugin/plugin.json | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-006 | Plugin and registry metadata currency | Plugin Metadata | .codex-plugin/plugin.json; server.json | Codex plugin and MCP registry manifests | Marketplace integrator | As a marketplace integrator, I want plugin metadata to match live discovery, so that the listing does not describe deployed tools as future work. | Metadata uses current versions and describes TripCode/River as discovery-visible, gated, and evidence-dependent. | Metadata called TripCode/River a near-term extension despite public discovery exposure. | Fixed | Static contract comparison and executable regression | Parse manifests and compare descriptions with tools/list. | FAIL — manifest posture contradicted live discovery. | Marketplace metadata drift. | Medium | Yes | Bumped plugin to 0.2.7 and server metadata to 1.1.8; corrected semantic and TripCode posture. | .codex-plugin/plugin.json; server.json | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-007 | Quickstart live checkpoint | Developer Quickstart | quickstart.md | Quickstart contract checkpoint | Developer | As a developer, I want the quickstart checkpoint to match current discovery, so that my first integration assumptions are correct. | Quickstart identifies the July 16 checkpoint and current route/tool/pricing/field counts. | Quickstart remained dated June 19 and reported 48 paths. | Fixed | Static contract comparison and executable regression | Compare frontmatter and checkpoint with live discovery. | FAIL — quickstart date and path count were stale. | Onboarding documentation drift. | Medium | Yes | Updated the checkpoint to July 16 and included 68/81/26/30/47 discovery counts. | quickstart.md | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.
PUB-008 | Human, LLM, RSS, and Atom changelog synchronization | Changelog | changelog.html; changelog-llm.html; rss.xml; atom.xml | Changelog surfaces and feeds | Subscriber and agent | As a subscriber or agent, I want every changelog surface to expose the same latest TripCode, so that human and machine readers share one release history. | Human, LLM, embedded JSON/XML, RSS, and Atom surfaces expose entry 203 with synchronized statistics. | The July calculation-plane and semantic MCP publication had no changelog entry or feed item. | Fixed | Static contract comparison and executable regression | Parse all changelog surfaces and assert entry 203 and synchronized statistics. | FAIL — publication event was absent from changelog surfaces. | Release provenance gap. | High | Yes | Added TripCode entry 203, synchronized counts to 203/117/200/203, and regenerated both feeds. | changelog.html; changelog-llm.html; rss.xml; atom.xml | 618ba15 | Parse public HTML/JSON/XML; compare documented OpenAPI and MCP counts with captured live discovery; run Circle buyer and MCP adapter tests. | PASS — public artifacts parse; feeds and machine contracts are synchronized; live discovery confirms 68 paths / 81 tools / 26 semantic tools; buyer tests pass 4/4; Go adapter packages compile. | Verified | No | Evidence: qa_evidence/commands/public-contract-refresh-20260716/. Canonical backend receipts: aitrailblazer-web-intel-mcp/qa_evidence/commands/current-deltasignal-audit-20260715/final_live_receipts.json. | Fix what is needed and finish.

## Dashboard
Feature QA Audit Dashboard
Metric | Value | Severity | Open Count
Tracked Features | 8 | Critical | 0
Current Verified | 0 | High | 6
Failed Test | 0 | Medium | 2
Fix In Progress | 0 | Low | 0
Fixed | 8 | Needs Product Decision | 0
Final Verified | 8 | Rows With Commit Hash | 8
Blocked | 0
Use Tracker as the working sheet. Dashboard formulas summarize the current audit state automatically.

## Lists
Allowed Status | Allowed Severity | Suggested Test Type
Not Reviewed | Critical | Code Review
Story Drafted | High | Manual UI
Ready For Test | Medium | Automated Test
Failed Test | Low | Smoke Test
Fix In Progress | None | Regression Test
Fixed |  | Accessibility Review
Retest Failed |  | Responsive Review
Verified |  | Integration Test
Blocked
Needs Product Decision

## Instructions
Feature QA Workbook Guide
Step | Instruction
1 | Keep Tracker as the single source of truth and do not create competing trackers.
2 | Create one row per user-visible feature or critical behavior. User stories describe how a user uses the feature, not how the implementation works.
3 | Use Status during discovery and testing, then use Final Status after retest.
4 | Record commit hashes in column S for any row touched by a fix or follow-up pass.
5 | Use Lists sheet values for Status, Severity, Test Type, and Final Status to keep reporting clean.
6 | Append a dated note to CHANGELOG.md after each completed QA or improvement pass.
7 | Keep the CSV, XLSX, and HTML companion aligned after every tracker update.
8 | Open the Dashboard tab for a quick pass/fail snapshot before closing the loop.